## Slide 1
  HOW AGILE WILL RUN IN OHB (SCRUMBAN)
Executive proposal for a controlled Scrumban operating model
One shared team • Multiple products • Quarterly outcomes • Evidence-based flow
  OCTOBER 2026

## Slide 2
Executive Agenda
From strategic need to operating decisions
1
Why this model
2
How work moves
3
How priorities are set
4
How delivery runs
5
What management decides
Management outcome
A clear operating model that separates strategic commitment, product priority, delivery sequencing, and technical execution, while preserving OHB controls and evidence.
The objective is not “more Agile ceremonies”; it is faster learning with clearer commitments and stronger control.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Executive Summary and Sections 2, 5 and 9. [/Sources]

## Slide 3
Why OHB needs a tailored model
The operating challenge is broader than a single Scrum product
Multiple products
Independent backlogs and Product Owners compete for one delivery pool.
Mixed work classes
MVP development, enhancements, UAT, defects and production support consume the same capacity.
Fixed management horizons
Management needs quarter-level outcomes while detailed scope continues to evolve.
Regulated delivery
Security, Risk, Compliance, CX, VAPT, CAB and audit evidence must be integrated, not deferred.
Selected response: Scrum cadence + Kanban flow controls + DevOps ownership + OHB governance.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 1, 2.1, 4.1, 16, 21 and 23. [/Sources]

## Slide 4
The operating premise
Agile values are translated into OHB delivery behaviours
People & collaboration
Direct decisions and continuous business participation
Working software
Progress evidenced by integrated, tested functionality
Responsiveness
Detailed scope may evolve inside approved boundaries
Sustainable quality
Controls, quality and supportability built into delivery
OHB DELIVERY PRINCIPLES
Outcome before output
Finish before starting more
Variable scope with explicit trade-offs
Controls by design
Visible constraints
Evidence as work progresses
Measure the system
Validate early and continuously
Notes: [Sources] OHB Agile Delivery Framework v0.1, Section 5 and Annexure A. [/Sources]

## Slide 5
The selected OHB operating model
Scrumban at team level, governed through quarterly portfolio decisions
Quarterly governance
Select outcomes, capacity and commitment categories.
Scrum cadence
Plan, review and improve through timeboxed cycles.
Kanban flow
Pull ready work, limit WIP and expose aging or blockers.
DevOps ownership
Build, deploy, monitor, support and improve what the team delivers.
One stable cross-product team; one consolidated roadmap; separate product backlogs; one shared delivery queue.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 4.1, 6, 13, 15 and 19. [/Sources]

## Slide 6
Governance follows the decision horizon
Decisions are made at the lowest appropriate level
Annual / demand
Approve needs and funding direction
Corporate approval authority > ExCom
Quarterly portfolio
Select goals and allocate scarce capacity
Agile Management Group
Product / feature
Order value within approved objectives
Product Owner
Sprint
Set Sprint Goal and select feasible ready work
Scrum Team
Daily flow
Pull the next eligible item and manage WIP
Development Team
Management chooses outcomes; Product Owners choose value order; the team chooses the feasible plan and technical sequence.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 7, 8, 9, 11 and 13.1.1. [/Sources]

## Slide 7
End-to-end lifecycle
Demand is progressively clarified before delivery commitment
DEMAND
Problem, sponsor, target outcome
PIPELINE CANDIDATE
Discovery and uncertainty reduction
FORECAST / STRETCH
Planning-ready; indicative quarter
COMMITTED
Capacity allocated; integrated plan approved
DELIVERY
Sprint goals + pull flow
RELEASE
UAT, controls, CAB, production
VALUE
Stabilization and KPI review
G1
Demand approval
G2
Discovery readiness
G3
Quarterly planning
G4
Story ready
G5
UAT accepted
G6
Release ready
Readiness increases by stage; detail is added only when needed for the next decision.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 3, 6.2, 11, 13.1.4, 14 and 26. [/Sources]

## Slide 8
How management sees the roadmap
Committed
What OHB expects to deliver. Quarterly planning confirms mandatory MVP scope, capabilities, dependencies, controls, testing, release activities and confirmed capacity.
Forecast
Planning-ready work OHB intends to pursue if capacity or another explicit condition is met. Shown separately and excluded from commitment-reliability reporting.
Pipeline Candidate
Approved demand still undergoing discovery or refinement. Show discovery timing and decision date, not a production commitment.
Decision required
Adopt this management view.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Section 6.2. Prioritization working discussion: proposed management simplification into Committed Goal, Stretch Goal and Pipeline Candidate. [/Sources]

## Slide 9
Protect the MVP boundary
Commit the outcome and mandatory feature groups, not every detailed story
MANDATORY
MVP
STRETCH MVP
POST-MVP ENHANCEMENTS
Mandatory MVP
Required for the approved objective, KPI, control or viable user journey.
Stretch MVP
Valuable but deferrable while preserving the MVP objective.
Post-MVP Enhancements / Standard Work
Further improvements and automation that are not required for first productive use.
A scope addition must create a visible trade-off: defer other scope, use approved contingency, or revise the forecast.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 5, 6.4, 11.2 and 13.2.1. [/Sources]

## Slide 10
Prioritization happens at three connected levels
One universal score should not be used from demand to story
1. QUARTERLY PORTFOLIO
MVP goals, material enhancements, technical enablers
Agile Management Group
Output: Committed / Forecast / Candidate
2. PRODUCT & FEATURE
Mandatory MVP, Stretch MVP, post-MVP features
Product Owner
Output: ordered feature groups
3. SPRINT & FLOW
Ready stories, defects, enablers and operational work
Scrum Team / Development Team
Output: Sprint Goal + shared Ready Queue
Approved demand does not equal permission to start; readiness and capacity precede commitment.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 9, 11.2, 13.1.1 and 13.2.2. Prioritization working discussion: three-level prioritization model. [/Sources]

## Slide 11
Decision: how should cross-product priority be resolved?
Three viable operating options
A. Executive-led quarterly order
The Agile Management Group ranks outcomes quarterly; weekly replenishment executes within those boundaries.
Strength
Clear authority; low meeting overhead
Risk
Can become slow if quarterly boundaries are too broad
RECOMMENDED
B. Capacity envelopes
Management allocates capacity by work purpose or selected products; Product Owners order within each envelope.
Strength
Protects UAT, operations and engineering work
Risk
Percentages can become rigid entitlements
C. Product Owner alignment forum
Product Owners collectively maintain the near-term queue; unresolved conflicts escalate.
Strength
Strong transparency and shared ownership
Risk
Consensus risk and potential duplication of governance
Notes: [Sources] Prioritization working discussion based on OHB framework roles and governance. OHB Agile Delivery Framework v0.1, Sections 7.5, 8, 9 and 11.2. [/Sources]

## Slide 12
Recommended operating mechanism
One shared Ready Queue, replenished through explicit procedures
PRODUCT BACKLOGS
POs order value
READINESS GATE
Definition of Ready
REPLENISHMENT
Admit work within capacity
SHARED READY QUEUE
Top eligible items
PULL
Developers pull when WIP allows
Replenishment Facilitator
Scrum Master administers the queue and enforces procedures; does not decide business value.
Cross-product change rule
Material queue changes require collective agreement or Agile Management Group escalation.
Continuity
Documented procedures, visible decision records and a delivery-side deputy remove key-person dependency.
Product Owners cannot inject work directly; the team should never have to guess what to pull next.
Notes: [Sources] Prioritization working discussion and screenshots supplied by the user: shared queue, gatekeeper de-risking, replenishment and continuity ideas. OHB Agile Delivery Framework v0.1, Sections 7.2, 7.3, 9, 15 and Annexure L. [/Sources]

## Slide 13
How the next item is selected
A policy stack reduces lobbying and constant re-sorting
1
AUTHORIZED
Belongs to an approved goal or service class
2
READY
Meets the applicable entry evidence
3
SERVICE CLASS
Expedite, Fixed Date, Committed, Operational, Enabler or Stretch
4
CAPACITY
Relevant WIP limit and reserve allow entry
5
ORDER
Goal contribution, urgency, risk, dependency, size and learning
6
DISPLACEMENT
Any injection identifies affected work and forecast impact
Tie-breaker only
FIFO applies only where items are otherwise equivalent.
Notes: [Sources] Prioritization working discussion based on service classes, readiness, WIP and visual ordering. OHB Agile Delivery Framework v0.1, Sections 15, 16 and 17. [/Sources]
1. Authorized: Is the work allowed to consume capacity?
First confirm that the item belongs to an approved source of work, such as:
a Committed Goal;
an approved Stretch Goal;
an operational or production-support reserve;
a Technical Enabler allocation;
an authorized Fixed-Date obligation;
a valid Expedite item.
Example: A user story for automated demand notifications is authorized because notifications are part of the approved Demand Management MVP.
If a Product Owner introduces an unrelated enhancement that was not included in the approved goal or capacity envelope, it does not proceed merely because the Product Owner considers it important.
2. Ready: Is there enough information to start responsibly?
The item must meet the applicable Definition of Ready. For a user story, this normally means:
the expected outcome is clear;
acceptance criteria are testable;
the story is appropriately sized;
dependencies are understood;
required access, data and environments are identified;
no unresolved issue prevents meaningful commencement.
Example: The notification story is authorized, but it cannot proceed if the recipient rules and trigger conditions have not been defined.
Authorized means OHB permits the work. Ready means the team can responsibly start it.

## Slide 14
Estimation matures with the decision
Estimate coarsely early; forecast empirically as delivery evidence grows
Demand / Candidate
XS–XL + uncertainty
Discovery need and broad feasibility
MVP / Quarter Goal
Mandatory feature-group sizes + dependencies
Quarterly scenario and commitment
Feature / Enhancement
XS–XL + reference feature + value inputs
Quarterly fit and trade-offs
User Story
Small / Medium / Too Large; points optional
Story splitting and Sprint selection
Technical Task
Optional hours or no estimate
Immediate coordination only
Delivery System
Throughput + cycle-time distributions
Probabilistic future forecasts
Estimate informs forecast; forecast informs commitment; an estimate is never a commitment.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Section 17. Estimation working discussion: progressive estimation by backlog layer. [/Sources]

## Slide 15
Capacity is planned by work classes
The team cannot assume 100% of capacity is available for new feature development
70%
20%
10%
Planned MVP / features
UAT & release support
Operations / urgent work
Option 1: Work-type envelopes
Protect operations, UAT and engineering enablement. Rebalance quarterly using actual consumption.
Option 2: Temporary product envelopes
Use only when two major products must progress concurrently and both have sufficient ready work.
Avoid permanent PO quotas
Permanent percentages create silos, idle capacity and political entitlement.
Decision required: approve the pilot capacity hypothesis and whether engineering enablement receives an explicit reserve.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 17.1 and 17.2. Prioritization screenshot discussion: capacity-allocation bucket method, adapted for OHB. [/Sources]

## Slide 16
Quarterly planning sets boundaries; Sprints adapt the route
The quarter is outcome-led, while detailed stories emerge progressively
QUARTERLY PLAN
Goal, mandatory features, capacity, controls and production target
FEATURE REFINEMENT
Break features into testable slices; confirm routes and dependencies
BACKLOG REPLENISHMENT
Admit ready work into one ordered team queue
SPRINT PLANNING
Set one primary Sprint Goal and select conservative work
SPRINT EXECUTION
Pull, limit WIP, review aging and unblock flow
SPRINT REVIEW
Validate increment; feedback returns to ordered backlog
New ceremony to add: Backlog Replenishment before Sprint Planning or on a weekly cadence.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 11.2, 13.1.2, 13.2 and Annexure S. Proposed addition: Backlog Replenishment Meeting. [/Sources]

## Slide 17
Delivery cadence and ceremonies
Every event has a distinct decision purpose
Quarterly Planning
Approve goals, classifications, capacity and control windows
Backlog Replenishment
Keep the shared Ready Queue ordered and within WIP
Sprint Planning
Set Sprint Goal and select feasible ready work
Daily Flow Review
Focus on completion, aging, blockers and WIP
Refinement
Prepare the next ready backlog slice
Sprint Review
Inspect working software and order feedback
Retrospective
Commit to one or two system improvements
Notes: [Sources] OHB Agile Delivery Framework v0.1, Section 13.2 and Annexure S. Proposed addition: Backlog Replenishment Meeting. [/Sources]

## Slide 18
Delivery workflow and control gates
Controls are integrated throughout the flow, not applied only at the end
Ready
Active Dev
Code Review
Technical Test
PO Validation
Feature / UAT
Release Ready
Live
Story Ready
Entry evidence
Maker-checker
Code quality
Story Accepted
Business behaviour
UAT Accepted
End-to-end evidence
Release Ready
Controls + rollback
MVP Live
Production validation
Route A: Independently testable
Story-level PO and tester validation; feature and release regression.
Route B: Connected story
Full validation when connected stories form a usable feature.
Route C: Technical enabler
Technical acceptance, then consuming-feature and release assurance.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 13.3, 14, 15, 23 and 24. [/Sources]

## Slide 19
Non-MVP work is controlled through service classes
Urgent and operational work remains visible and consumes real capacity
EXPEDITE
Critical outage, material security/data issue or blocker to committed release
Global WIP limit: 1; show displaced work
FIXED DATE
Regulatory or immovable operational date
Sequence by latest responsible start
OPERATIONAL
Support and defects for products the team operates
Reserve capacity; triage by severity
TECHNICAL ENABLER
Infrastructure, CI/CD, licensing, automation and engineering controls
Plan explicit capacity; do not treat as spare-time work
STANDARD
Normal enhancements, defects and routine technical work
Pull from the ordered Ready Queue
SPIKE
Reduce a material unknown
Time-boxed question, evidence and decision
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 16 and 17.2. Prioritization discussion: adapted service classes and technical-enablement treatment. [/Sources]

## Slide 20
Accountability remains clear
No single gatekeeper owns all business priorities
Agile Management Group
Cross-product priorities, quarterly commitments and material displacement
Product Sponsor
Business outcome, sponsorship and senior business decisions
Product Owner
Product backlog order, expected behaviour and acceptance
Scrum Master
Flow steward, replenishment facilitator and policy enforcement
Development Team
Sizing, technical sequence, execution, quality and supportability
Shared Functions
Applicability, lead times, reviews, approvals and enabling services
Queue administration is a process role; business priority remains with the appropriate Product Owner or portfolio authority.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 7 and 9. Prioritization discussion: gatekeeper de-risked through a neutral facilitator, documented policies and deputy. [/Sources]

## Slide 21
Management view: outcomes, reliability and flow
Measures improve the system; they do not rank individuals
OUTCOMES
MVP milestone reliability
Adoption and turnaround
Benefit realization
PREDICTABILITY
Committed feature delivery
Sprint Goal achievement
Forecast range vs actual
FLOW
Throughput
Cycle time
Work-item age
Blocked-time ratio
QUALITY & CAPACITY
UAT leakage
Escaped defects
Operational consumption
UAT consumption
Prohibited management measures: individual velocity, lines of code and AI prompt counts.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Section 18. [/Sources]

## Slide 22
Pilot before institutionalizing the model
Use one representative product to test the operating system and close open decisions
1
Framework alignment
2
Pilot selection
3
Candidate discovery
4
Engineering readiness
5
Stakeholder buy-in
6
Pilot execution
7
Framework approval
Pilot evidence
Flow, quality, participation, controls, actual support demand and delivery reliability.
Decisions closed
Queue policy, capacity reserves, service classes, tooling, CI/CD, test evidence and release route.
Scale trigger
Reassess team structure only when multiple stable product-aligned teams and recurring cross-team dependencies exist.
The pilot validates the operating model; it is not only a product delivery trial.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Sections 26, 28 and 29. [/Sources]

## Slide 23
Management decisions requested
Approve the model direction and authorize the pilot to resolve detailed operating choices
1
Operating model
Adopt Scrumban with DevOps ownership and OHB-specific governance.
2
Roadmap language
Choose Committed / Stretch / Pipeline or retain Committed / Forecast / Candidate.
3
Prioritization model
Approve executive quarterly ordering + weekly replenishment as the baseline.
4
Capacity policy
Approve pilot reserves and decide whether engineering enablement has an explicit envelope.
5
Queue governance
Approve one shared Ready Queue, neutral facilitator and cross-product change rule.
6
Pilot
Authorize Sprint 0 and one controlled representative product pilot.
Approval sought: framework direction, decision options, and a pilot mandate with evidence-based refinement.
Notes: [Sources] OHB Agile Delivery Framework v0.1, Executive Summary, Sections 26 and 28. Prioritization and estimation working discussions. [/Sources]

## Slide 24
CONTROLLED AGILITY FOR OHB
Clear outcomes. Visible trade-offs. Faster learning. Stronger evidence.
Q & A
Notes: [Sources] OHB Agile Delivery Framework v0.1. [/Sources]